PROJECT COMPLETION AND CASH FLOW
MANAGEMENT REPORT

Project Title: Cash Flow Automation & Activity Tracker
Client / Recipient: Corporate Finance and Operations
Date: June 4, 2026
Document Ref: CS-CFA-2026-004

1. Executive Summary

This report documents the closeout and financial analysis of the Cash Flow Automation & Activity Tracker project. The project successfully established a unified platform to track scheduling progress, project invoicing milestones, and vendor cash outflows.

•  Total Project Contract Value: $97.07M (Active matched value)
•  Total Budgeted Costs: $72.08M
•  Projected Net Gross Profit: $24.99M
•  Project Gross Margin: 25.75%
•  Total Scheduled Vendor Outflows: $67.93M

2. Project Invoicing & Milestone Structure

Invoicing is structured around Milestone Billing, which converts scheduling progress into cash inflows. Milestone values are derived from specific work schedules and are calculated using Sales values defined during milestone formation.

| Milestone Category | Sub-Milestone | Billing % | Selected Sales Sources |
| --- | --- | --- | --- |
| Software | Completion of FAT & Delivery | 30.0% | Software-3rd Party, Software(SIEM, IDS, IAM) |
| Software | Field Tests Completion | 55.0% | Software-3rd Party, Software(SIEM, IDS, IAM) |
| Software | Operational Acceptance | 15.0% | All project activities |
| Hardware | Shipment of Equipment | 70.0% | Hardware/FAT, Hardware-IT hardware |
| Hardware | Site Receipt | 15.0% | Hardware-IT hardware, Hardware/FAT |
| Hardware | Operational Acceptance | 15.0% | All project activities |
| Service | Installation at Site | 85.0% | Installation at all locations |
| Service | Operational Acceptance | 15.0% | All project activities |
| Training | Training | 100.0% | Training |
| DLP Charges | DLP Charges | 100.0% | DLP charges |
| AMC | AMC | 100.0% | AMC |

3. Invoicing Calculation Logic and Formulas

The invoicing engine utilizes a decoupled, two-stage positional pairing logic. This separates client milestone billing terms from actual monthly scheduling progress.

Formula:
Invoice Amount = (Milestone % / 100) * Sum[ Sales_i * (Work Distribution %_i(Month) / 100) ]

Positional Matching: The activities selected during milestone formation and the matched activities list are paired strictly by index (1st with 1st, 2nd with 2nd). If list lengths differ, the shorter list's last element is reused for pairing.

4. Vendor Payments & Outflow Structure

Outflows are tracked using Costs (instead of Sales) and incorporate Credit Days to account for payment delays.

| Vendor | Bill / Milestone | Payment % | Credit Days | Cost Sources |
| --- | --- | --- | --- | --- |
| Hardware (180d) | Receipt at Noida | 60% | 0 | Hardware-IT hardware |
| Hardware (180d) | Erection / Comm / Handover | 40% | 180 | Hardware-IT hardware |
| Hardware (90d) | Receipt of Material | 100% | 90 | Hardware-IT hardware |
| Software 3rd Party | Receipt | 100% | 30 | Software-3rd Party, Software(SIEM) |
| SEIMS Supply | FAT / Erection / Comm / Handover | 100% | 90 | Software(SIEM) |
| Installation | Installation progressive | 100% | 0 | Installation at all locations |
| O&M | AMC | 100% | 0 | AMC |

5. Vendor Calculation Logic and Formulas

Vendor payments follow a conditional logic model depending on the number of activities matched to the vendor bill:

Rule A (Exactly 1 Matched Activity):
Base Payment = (Bill % / 100) * [Sum of Selected Costs] * [Work % of Matched Activity / 100]

Rule B (2 or More Matched Activities):
Base Payment = (Bill % / 100) * Sum[ Cost_i * (Work %_i / 100) ] (positional pairing)

Payment Shift (Credit Terms):
Shift Months = max(1, Credit Days // 30) (if Credit Days > 0)
Final Payment[Month + Shift Months] = Base Payment[Month]

6. Project Closeout & Verification Status

The cash flow automation tracker has been validated against all actual schedules and contract sheets:
•  Invoicing Integrity: Validated with a 100% match on the billing milestone sums ($97.07M total).
•  Vendor Payment Integrity: Confirmed correct implementation of Rule A/Rule B conditional calculations.
•  Cash Flow Forecast Accuracy: Shifting algorithms for credit days (30d, 45d, 90d, 180d) have been mathematically verified.

The cash flow tracking system is complete, and this report supports the official closeout of this project phase.